## Sheet1
Week | Date | Iteration | Cox | Jaffer | Port | All
6 | Jun 22 | FP4 | Write config/database.php: DB connection setup and shared utilities | Write schema migration SQL: sessions, conversation_log, domain_state tables with constraints | Write schema migration test: verify tables, UNIQUE token constraint, JSON round-trip in domain_state | MILESTONE: Database Scaffolding & System Initialization Establish full relational schema - sessions, conversation_log, domain_state. Every agent depends on this layer; building it first means all subsequent modules test against real persistence, not mocked data. Integration; promote to GitHub; all in sync
7 | Jun 29 | FP5 | Implement createSession() and readSession() in InterviewSession.php | Implement writeExchange() and readTranscript() methods in InterviewSession.php | Implement writeDomainState() and readDomainState(); run atomic transaction recovery test | MILESTONE: Snapshot Agent & Session Persistence Build InterviewSession.php. The LLM has no memory between API calls - this agent makes the system stateful by persisting every exchange and domain state update across turns. Integration; promote to GitHub; all in sync
8 | Jul 6 | FP6 | Build RequirementParser.php: construct extraction prompt, inject user message + domain JSON, call LLM in JSON mode | Implement response validation: parse and validate returned JSON against 8-domain schema, write to DB | Implement programmatic gate check (all 8 COVERED -> trigger Compiler); run Shopify API verification proof | MILESTONE: Extraction Agent & LLM Semantic Evaluation (Step 1) Build RequirementParser.php. LLM maps user text to 8 domains using JSON mode. After each extraction, the programmatic gate checks if all 8 are COVERED - if yes, skip routing and trigger the Compiler directly. Integration; promote to GitHub; all in sync
9 | Jul 13 | FP7 | Build AgentEngine.php: construct routing prompt, inject transcript + domain state, call LLM API | Implement in-scope routing branch: LLM generates domain-targeting question for next OPEN domain | Implement out-of-scope routing branch (drift redirection, no domain advance); run boundary deviation test | MILESTONE: Routing Agent & Adaptive Question Generation (Step 2) Build AgentEngine.php. Single LLM call classifies input and generates response - in-scope routes to a domain-targeting question, off-scope routes to drift redirection without advancing any domain state. Integration; promote to GitHub; all in sync
10 | Jul 20 | FP8 | Build HTML skeleton of public/index.php: Bootstrap 5 split-pane layout with both panel containers | Style and wire left chat panel: agent/user message bubbles, text input field, submit button | Build right domain matrix panel: 8 data-domain badges + progress bar; verify responsive at 1440/768/375px | MILESTONE: Workspace Interface Construction Build public/index.php - Bootstrap 5 split-pane layout with live chat stream (left) and domain coverage matrix (right). Each badge uses data-domain attributes for independent JS targeting. Verify at 3 breakpoints. Integration; promote to GitHub; all in sync
11 | Jul 27 | FP9 | Build public/endpoint.php: sequential chain controller - Extraction -> gate -> Routing or Compiler | Build public/js/app.js: UI lockdown on submit (spinner), single AJAX POST, unlock + update badges on response | Run race-condition stress test: confirm single network request per submit in DevTools; verify single server execution per submit | MILESTONE: Async Pipeline & Chain Execution Controller Build endpoint.php (chain controller) and app.js (UI lockdown + AJAX). UI lockdown prevents concurrent requests - without it, parallel chain executions writing to domain_state simultaneously corrupt coverage. Integration; promote to GitHub; all in sync
12 | Aug 3 | FP10 | Build ManifestGenerator.php: read finalized 8-domain data from DB, populate 5-prompt build plan template | Implement placeholder substitution: replace all template vars with user's verified answers; wire output into right panel transition | Run filler-pattern regex scan on output; validate 5 labeled prompt sections with non-empty domain-specific content | MILESTONE: Compiler Agent & Prompt Build Plan Generation (Step 3) Build ManifestGenerator.php. When all 8 domains are COVERED, reads finalized data and outputs a sequenced 5-prompt build plan. Right panel transitions from domain matrix to copy-ready plan. Integration; promote to GitHub; all in sync
13 | Aug 10 | FP-Final | Build validate_manifest.php: Stage 1 validator - 5 prompt sections present, non-empty content, zero filler patterns | Execute full loop integration test: raw idea in -> 5-prompt plan out; document any chain integration failures | Run Stage 2 success story: paste Prompt 1 into Claude Code, document result; prepare final presentation demo walkthrough | MILESTONE: End-to-End Validation & Success Story Stage 1 - validate_manifest.php confirms all 5 prompt sections populated with zero filler. Stage 2 - Prompt 1 pasted into Claude Code begins building a working prototype with no structural clarifying questions. Integration; promote to GitHub; all in sync
Note: | All artifacts (docs, schema files, design docs, code) must turn up on GITHUB each week.
Only Weekly Signoff should be submitted by each student to D2L.
Reference: | Interview Questions
1. What is the problem you are trying to solve?
2. What are the data sources?
3. How do you get the data out of the data sources?
4. Is it structured data? Or unstructured data?
5. What are the series of questions?